## iApply_Integration_Overall_Stat
Form # | Form Code | iApply Form Name | Hearing Data Integration | File Allocation (Delegates & Case Manager Details) Integration | Attachment Integration | New Licence Creation Integration | Entity Integration | LSA/LSL Integration | DOC Gen Integration | Financial Transaction Integration | Testing Status (Buisness) | Overall Integration Status | Planned Production Date | LOGIC_PROD Updation Date | Additional Notes
1 | MAL | Relocate a License / Move a Licence | COMPLETE | COMPLETE | COMPLETE | NOT REQUIRED | NOT REQUIRED | LSA ONLY [ COMPLETED] | COMPLETE | COMPLETE | COMPLETED | COMPLETE | - | LIVE - 23 Sep 2021 [1:35 PM] | BATCH 1 NO ENTITIES
2 | ARE | Change Alter or Redefine a Licensed Premises | COMPLETE | COMPLETE | COMPLETE | NOT REQUIRED | NOT REQUIRED | LSA ONLY [ COMPLETED] | COMPLETE | COMPLETE | COMPLETED | COMPLETE | - | LIVE - 23 Sep 2021 [1:35 PM] | BATCH 1 NO ENTITIES
3 | VCD | Variation To Conditions (downgrade) / Downgrade a License | - | - | - | - | - | - | - | - | - | - | 2022-05-13 | - | BATCH 1 NO ENTITIES
4 | VCU | Variation To Conditions (upgrade) / Upgrade a Licence | - | - | - | - | - | - | - | - | - | - | 2022-05-13 | - | BATCH 1 NO ENTITIES
5 | VAR | Vary trading rights | COMPLETE | COMPLETE | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | LSA ONLY [ COMPLETED] | COMPLETE | COMPLETE |  | COMPLETE
6 | WAG | Application For The Approval Of Wagering Systems/Equipment | - | - | - | - | - | - | - | - | - | - | 2022-01-21 | - | BATCH 1 NO ENTITIES
7 | ROB | Application To Review a Barring Order | - | - | - | - | - | - | - | - | - | - | 2022-01-07 | - | BATCH 1 NO ENTITIES
8 | COD | Notify the Commissioner of Change in Details | COMPLETE | COMPLETE | COMPLETE | NOT REQUIRED | NOT REQUIRED | LSA ONLY [ COMPLETED] | COMPLETE | COMPLETE | COMPLETED | COMPLETE | 2022-12-24 | LIVE - 30 March 2022 [3:00 PM] | BATCH 1 NO ENTITIES
9 | CAP | Casino application for approval | - | - | - | - | - | - | - | - | - | - | 2022-04-29 | - | BATCH 1 NO ENTITIES
10 | GSL | Offer to Sell Gaming Machine Entitlements | - | - | - | - | - | - | - | - | - | - | 2022-05-27 | - | BATCH 1 NO ENTITIES
11 | IDG | Application To Increase or Decrease Gaming Machines | - | - | - | - | - | - | - | - | - | - | 2021-12-10 | - | BATCH 1 NO ENTITIES
12 | RDW | Application For Review Of Decision To Withhold Winnings | - | - | - | - | - | - | - | - | - | - | 2022-04-15 | - | BATCH 1 NO ENTITIES
13 | GMM | Application For The Approval Of Game Machine Modification | - | - | - | - | - | - | - | - | - | - | 2022-04-01 | - | BATCH 1 NO ENTITIES
14 | RWL | Renewal of a wagering licence | - | - | - | - | - | - | - | - | - | - | 2021-11-26 | - | BATCH 1 NO ENTITIES
15 | EMP | Employment of minors | COMPLETE | COMPLETE | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | LSA ONLY [ COMPLETED] | COMPLETE | COMPLETE | COMPLETED | COMPLETE | 2022-02-18 | LIVE -04 March 2022 [after 5:00 PM] | BATCH 1 NO ENTITIES
16 | GBY | Offer to Purchase Gaming Machine Entitlements | - | - | - | - | - | - | - | - | - | - | 2022-05-27 | - | BATCH 1 NO ENTITIES
17 | SOP | Offer to Purchase Gaming Machine Entitlements - Casino | - | - | - | - | - | - | - | - | - | - | 2022-05-27 | - | BATCH 1 NO ENTITIES
18 | COS | Offer to Sell Gaming Machine Entitlements - Club One | - | - | - | - | - | - | - | - | - | - | 2022-05-27 | - | BATCH 1 NO ENTITIES
19 | IDS | Application for an Interstate Direct Sales Licence | COMPLETE | COMPLETE | COMPLETE | COMPLETE | COMPLETE | LSA & LSL COMPLETE | COMPLETE | COMPLETE | COMPLETED | COMPLETE | 2021-10-29 | LIVE -02 Nov 2021 [5:25 PM] | BATCH 2 With Entity
20 |  | Interstate Betting Operators | - | - | - | - | - | - | - | - | - | - | 2022-03-04 | - | BATCH 2 With Entity
21 |  | Approval of a person (Gaming Machines Act 1992) (requires SAPOL portal integration) | - | - | - | - | - | - | - | - | - | - | 2022-06-24 | - | BATCH 2 With Entity
22 |  | Application for a Gaming Machine Service Licence (requires SAPOL portal integration) | - | - | - | - | - | - | - | - | - | - | 2022-06-24 | - | BATCH 2 With Entity
23 |  | Application for a Gaming Machine Dealer’s Licence | - | - | - | - | - | - | - | - | - | - | 2022-06-24 | - | BATCH 2 With Entity
24 |  | Application for a Bookmaker or Agent licence | - | - | - | - | - | - | - | - | - | - | 2022-06-24 | - | BATCH 2 With Entity
25 | SUB | Make a submission | NOT REQUIRED | NOT REQUIRED | COMPLETE | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | COMPLETE | NOT REQUIRED | COMPLETED | COMPLETE [2/11/2021] | 2021-11-12 | LIVE 26/05/2022 [3pm] | *depends on LGX release BATCH 2 With Entity
26 |  | Approval of an electronic drawing system | - | - | - | - | - | - | - | - | - | - | 2022-07-08 | - | BATCH 2 With Entity
27 |  | Change of directors – (Has PID) | - | - | - | - | - | - | - | - | - | - | 2022-07-08 | - | BATCH 2 With Entity
28 |  | Nomination of supervisor (no PID) – NEW FORM ((((PRIORITY FOR OCCUPATIONAL HIGH VOL)))) | - | - | - | - | - | - | - | - | - | - | 2022-07-22 | - | BATCH 2 With Entity
29 |  | Builders indemnity exemption | - | - | - | - | - | - | - | - | - | - | 2022-07-22 | - | BATCH 2 With Entity
30 |  | Administrators, Landlord or Mortgagee Taking Over a Licence | - | - | - | - | - | - | - | - | - | - | 2022-03-18 | - | BATCH 2 With Entity
31 | LLFIN | Lodge a financial statement | NOT REQUIRED | NOT REQUIRED | COMPLETE | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | COMPLETE | COMPLETE | COMPLETED | COMPLETE [30/11/2021] | 2022-12-10 | LIVE -09 DEC 2021 [5:00 PM] | BATCH 2 With Entity
32 |  | Notification to deploy and use an FRT System | - | - | - | - | - | - | - | - | - | - | - | - | -
33 |  | Renewal of a lottery licence | - | - | - | - | - | - | - | - | - | - | - | - | -
34 |  | Major lottery licence | - | - | - | - | - | - | - | - | - | - | - | - | -
35 |  | Major Bingo Licence | - | - | - | - | - | - | - | - | - | - | - | - | -
36 |  | Instant lottery licence | - | - | - | - | - | - | - | - | - | - | - | - | -
37 | ODO | Alter or replace an odometer | COMPLETE | COMPLETE | COMPLETE | NOT REQUIRED | NOT REQUIRED | NOT REQUIRED | COMPLETE | COMPLETE | COMPLETED | COMPLETE [3/02/2022] | 2022-02-15 | LIVE -15 FEB 2022 [5:00 PM]
38 |  | Trade promotion (instant) | - | - | - | - | - | - | - | - | - | - | - | - | -
39 |  | Trade promotion (Major) | - | - | - | - | - | - | - | - | - | - | - | - | -
| * | LSA - Updating LicenceSystemApplications Table
| * | LSL - Updating LicenceSystemLicences Table

## sp_view_prod_updation
Stored Procedure Name & View Name | Release 1 | Release 2 | Release 3 | Release 4 | Release 5 | Release 4
SQL Stored Procedures
spWebAddAppLinkGroup | Yes | Yes | YES | NO | -
spWebAddApprovalGamesMachines | Yes | Yes | YES | NO | -
spWebAddEntities | NO | NO | YES | NO | -
spWebAddLicencePostalDetails | NO | NO | YES | NO | -
spWebAddLicensees | NO | NO | YES | NO | -
spWebAddNote | Yes | Yes | YES | NO | -
spWebAddOnlineFinancialTransaction | Yes | Yes | YES | NO | -
spWebApplicationDocuments | Yes | Yes | YES | NO | -
spWebDecisionAppAddApplication | Yes | Yes | YES | NO | -
spWebDecisionAppAddLSA | Yes | Yes | YES | NO | -
spWebDecisionAppAddLSL | NO | NO | YES | NO | -
spWebDecisionAppAddOrderDocument | Yes | Yes | YES | NO | -
spWebDecisionAppOrderFinaliseDraft | Yes | Yes | YES | NO | -
spWebDecisionAppReallocateFile | Yes | Yes | YES | NO | -
spWebDecisionAppUpdateFees | Yes | Yes | YES | NO | -
spWebGetEntityDetails | NO | NO | YES | NO | -
spWebPreferredDeliveryMethodLiquor | NO | NO | YES | NO | -
spWebSendNotification | Yes | Yes | YES | NO | -
spWebTmpAddApplication | NO | NO | YES | NO | -
spWebAddObjections | NO | NO | YES | NO | -
spWebiApplyHelpers | NO | NO | YES | NO | -
spWebGetLotteryDetails | NO | NO | YES | NO | -
spWebAddCCSTablesToLOGIC | NO | NO | NO | YES
Views
vwWebApplicationTypes | NO | NO | YES | - | -
vwWebEntityTypes | NO | NO | YES | - | -
vwWebLicenceAll | NO | NO | YES | - | -
vwWebLicenceClasses | NO | NO | YES | - | -
vwWebDecisionAppApplicationData | NO | NO | yes | - | -
vwWebCCS_Practice | NO | NO | NO | YES | -
vwWebCCS_Product | NO | NO | NO | YES | -

## Changes_To_Made
NO | Changes to be made for all the iApply forms/specific iApply form | iApply Form Name to be changed | Status [Form #] | Additional Notes
1 | Populating Financial Details to LOGIC (Only if iApply form contains Financial Transaction) | Only iApply Forms with Financial Transaction | COMPLETED
2 | Populating File Allocation Details to LOGIC | ALL | COMPLETED
3 | Change the value for 'Entered by' = 'NIDD' into 'iApply' in LOGIC | ALL | COMPLETED
4 | Remove time from Receipt Date in LOGIC (ONLY date) | ALL | COMPLETED
5 | Adding a message "iApply Customer reference Number- (LGO_referenceNumber)" - iApply APPID [eg 60da7c81ad9c5c11e86ab420] in Notes [APP_Notes] section in LOGIC | ALL | COMPLETED | Only LGO_referencenumber
6 | Adding an Attachment type 'Other' in LGX_UAT & LGX_PROD(Configuration of Attachment Type names) | ALL | COMPLETED
7 | Configuring Document type (Attachement Type) names in LGX_PROD & LGX_UAT | ALL | COMPLETED
8 | Populating Hearing Data into LOGIC and LGX | ALL | COMPLETED
9 | Populating values for apg_id_delegate & apg_id_case_manager to LOGIC | ALL | COMPLETED
10 | Populating values for GA_SellBuyEntitlementQTY in LOGIC | ALL | COMPLETED
11 | Adding Processing Times for each form | ALL | COMPLETED
12 | iApply form Link status | ALL | COMPLETED
13 | Licence lookup to return LSL_JSON record | ALL | COMPLETED
21 | Create API for a generic application status lookup feature to be added to the application dashboard in LGO (and elsewhere) so users can still track applications lodged via iapply | ALL | COMPLETED | PHP - api
22 | Review/update secureCBS table to see if any additional columns would be useful for reporting | ALL | COMPLETED
23 | Add ‘Customer Reference’ column to view submissions table | ALL | COMPLETED
24 | Review and update view submissions | ALL | COMPLETED
28 | APP_AdvertDateLast iApply form integration | ALL | COMPLETED
29 | Adding any number of Doc Gen types in the iApply form [configure it from iApply form without changing the back end [PHP file] | ALL | COMPLETED | Note * number of doc Gen may differ depending on the form some forms may contain payment summary and application summary only some may contain more than that (the php file need to handle that )
14 | Integrate the Barrings table to allow barrings to be added via future form | - | -
15 | Objections - Create objection records (Lodge a submission) | - | - | Add a application look up into the form and update object table and ApplicationObjections
16 | Decisions/Orders - Add ability to create an automated decision (triggered via form) | - | -
17 | Licence details - Add ability for form to write to licence details (eg premises contact details) | IDS | COMPLETED | FORM CODE [IDS]
18 | Notes - Add ability to add a note against licence/application (OBT_ID will need to be specified in the form) | ALL | COMPLETED | *Created App notes as a separate test form (Ability to add notes against any object type in LOGIC )
19 | Add ability to create person approval category records / PID screen records | - | -
20 | Add occupational related fields from applications table | - | -
25 | Set up failed Web service log + email notification + Integration error log | - | -
26 | Add fallback allocation if no users are a part of allocation group | - | -
27 | Sapol portal integration | - | -
30 | optimisation the call to iapply to get the docgens and attachments | ALL | - | at the moment it pretty slow
31 | AGM_CB_ID_InterstateApproval value is hard coded | WAG/GMM | - | GMM - Application For The Approval Of Game Machine Modification / WAG - Application For The Approval Of Wagering Systems/Equipment
32 | Adding Fee Types to iApply forms | All | - | 4 forms has been completed (MAL/VCD/VCU/ARE)
33 | Timeouts occurring for integration API calls | All | COMPLETED | Scott already raise this issue with DPC